## Project Overview
KIT502 Group Assignment — Project Task Overview
Project | Unit | Semester | Total Members | Start Date | End Date | Status
Event Organising System | KIT502 Web Development | 2026 Semester 1 | 4 | 05 Mar 2026 | 24 Mar 2026 | ✅ Completed
Team Members & Roles
Member | GitHub ID | Role | Responsibility | Assignment 1 Tasks | Commits | Status
YoungHyun Kim | JayKimyh | Backend + DB + PM | Project setup, DB design, Auth, Nav, Merge management | ERD/Schema, README, Login page, Signup validation, Nav bar | 22 | ✅ Done
Gunneet Kaur | guneet0526kaur-lang | Frontend Developer A | Public pages & layout | Landing page, Events page, CSS variables, Image assets | 8 | ✅ Done
Pragun Budhathoki | Pragun Budhathoki | Frontend Developer B | Event & Admin interfaces | Create Event, Manage Events, Admin Dashboard, JS validation, JSON data | 16 | ✅ Done
Sidd | (via JayKimyh commit) | Frontend Developer C | Authentication pages | Register page, Login page UI | 1 | ✅ Done
Assignment 1 Deliverable Checklist
# | Deliverable | Assigned To | Due | Completed Date | Status | Notes
1 | Site Navigation (all pages, hover/active CSS) | YoungHyun | Mar 24 | Mar 24 | ✅ Done | Consistent across all pages
2 | Landing Page (image, intro, 2 events) | Gunneet | Mar 20 | Mar 20 | ⚠️ Partial | Button text: 'View Details' instead of 'Buy Ticket'
3 | Registration Page + JS Validation (jQuery) | Sidd | Mar 22 | Mar 24 | ✅ Done | register_script.js added with full validation
4 | Login Page + JS Validation | Sidd | Mar 22 | Mar 23 | ✅ Done | login_script.js working
5 | Create Event Page + JS (alert + redirect) | Pragun | Mar 23 | Mar 24 | ✅ Done | create_event.js connected; Confirmed/Cancelled added
6 | Event Management (4 events, desc, organiser, time) | Pragun | Mar 23 | Mar 23 | ✅ Done | events.json required; descending sort implemented
7 | Admin Dashboard | Pragun | Mar 22 | Mar 23 | ✅ Done | admin_dashboard.js fetches users.json
8 | Database ER Diagram | YoungHyun | Mar 11 | Mar 24 | ✅ Done | Submitted as PDF
9 | Database Schema (SQL) | YoungHyun | Mar 11 | Mar 24 | ✅ Done | Fixed Mar 24
10 | ReadMe File | YoungHyun | Mar 12 | Mar 24 | ⚠️ Partial | Missing external resources list & timeline table

## Task List
KIT502 Assignment 1 — Detailed Task List
Task ID | Page / Module | Task Description | Assigned To | Category | Start Date | End Date | Status | Notes
T-001 | Project Setup | Initial repository creation & project folder structure | YoungHyun | Setup | 05 Mar | 09 Mar | ✅ Done | GitHub repo created
T-002 | Design System | Define CSS variables (colour palette, typography, spacing) | YoungHyun | Design | 07 Mar | 09 Mar | ✅ Done | variables.css — brand orange #E76F51
T-003 | Documentation | Write README.md, shared CSS guide, project structure docs | YoungHyun | Docs | 09 Mar | 12 Mar | ✅ Done | README describes all pages & roles
T-004 | Database Design | Create ER Diagram with entities, attributes, PKs/FKs, relationships | YoungHyun | Database | 11 Mar | 24 Mar | ✅ Done | Final fix committed Mar 24
T-005 | Database Design | Write Database Schema SQL with data types | YoungHyun | Database | 11 Mar | 24 Mar | ✅ Done | Submitted as PDF
T-006 | Figma Prototype | Create UI prototype in Figma and link in README | YoungHyun | Design | 11 Mar | 15 Mar | ✅ Done | Figma link in README
T-007 | Landing Page | HTML structure: hero section, nav, footer | Gunneet | Frontend | 15 Mar | 16 Mar | ✅ Done | index.html
T-008 | Landing Page | CSS styling: hero, event cards, responsive layout | Gunneet | Frontend | 15 Mar | 16 Mar | ✅ Done | landing.css
T-009 | Landing Page | Display 2 events with title, date, price | Gunneet | Frontend | 15 Mar | 20 Mar | ✅ Done | Static dummy events
T-010 | Landing Page | Change event card button to 'Buy Ticket' | Gunneet | Frontend | 20 Mar | — | ⚠️ Pending | Currently shows 'View Details'
T-011 | Events Page | HTML: event listing grid with filter panel | Gunneet | Frontend | 15 Mar | 16 Mar | ✅ Done | events.html — 6 events displayed
T-012 | Events Page | CSS: event cards, filter section, responsive grid | Gunneet | Frontend | 15 Mar | 16 Mar | ✅ Done | events.css
T-013 | Event Detail Pages | Create 6 individual event detail HTML pages | YoungHyun | Frontend | 22 Mar | 22 Mar | ✅ Done | Separated into event_details/ folder
T-014 | Register Page | HTML form: role, name, email, password, confirm password, register/reset btns | Sidd | Auth | 22 Mar | 22 Mar | ✅ Done | register.html
T-015 | Register Page | JS validation: empty fields, email format check | Sidd | Auth | 22 Mar | 24 Mar | ✅ Done | register_script.js via jQuery 3.7.1
T-016 | Register Page | JS validation: password match + policy (6 chars, upper, lower, special) | Sidd | Auth | 22 Mar | 24 Mar | ✅ Done | Password policy enforced
T-017 | Register Page | Reset button clears all fields; submit redirects to landing page | Sidd | Auth | 22 Mar | 24 Mar | ✅ Done | Redirect to index.html
T-018 | Login Page | HTML form: email, password, login button, link to register | Sidd | Auth | 22 Mar | 22 Mar | ✅ Done | login.html — fixed sign_up link
T-019 | Login Page | JS validation: empty field check, submit redirects to landing page | Sidd | Auth | 22 Mar | 23 Mar | ✅ Done | login_script.js
T-020 | Create Event Page | HTML form: title, desc, start/end date, location, capacity, price, status, img | Pragun | Event Mgmt | 16 Mar | 22 Mar | ✅ Done | create_event.html
T-021 | Create Event Page | Status dropdown options: Draft, Confirmed, Cancelled | Pragun | Event Mgmt | 22 Mar | 24 Mar | ✅ Done | Fixed Mar 24 (was missing Confirmed/Cancelled)
T-022 | Create Event Page | JS validation: empty fields, date order check | Pragun | Event Mgmt | 23 Mar | 23 Mar | ✅ Done | create_event.js
T-023 | Create Event Page | JS: alert 'New event has been created', redirect to manage_events.html | Pragun | Event Mgmt | 23 Mar | 23 Mar | ✅ Done | Implemented in create_event.js
T-024 | Create Event Page | Connect <script src='js/create_event.js'> to HTML | Pragun | Event Mgmt | 23 Mar | 24 Mar | ✅ Done | Script tag added to create_event.html
T-025 | Manage Events Page | HTML table: Event Name, Category, Description, Organiser, Date & Time cols | Pragun | Event Mgmt | 22 Mar | 23 Mar | ✅ Done | manage_events.html
T-026 | Manage Events Page | 4 dummy events in reverse chronological (descending) order | Pragun | Event Mgmt | 23 Mar | 23 Mar | ✅ Done | data/events.json with 4+ events
T-027 | Manage Events Page | Edit button: generate custom message via prompt dialog | Pragun | Event Mgmt | 23 Mar | 23 Mar | ✅ Done | editEvent() in manage_events.js
T-028 | Manage Events Page | Delete button: generate confirmation message | Pragun | Event Mgmt | 23 Mar | 23 Mar | ✅ Done | deleteEvent() with confirm()
T-029 | Manage Events Page | Link to Create Event Page | Pragun | Event Mgmt | 22 Mar | 22 Mar | ✅ Done | 'Create New Event' button in header
T-030 | Admin Dashboard | HTML layout: stats cards, user mgmt table, event mgmt table | Pragun | Admin | 22 Mar | 23 Mar | ✅ Done | admin_dashboard.html
T-031 | Admin Dashboard | JS: fetch users.json, render user table dynamically | Pragun | Admin | 23 Mar | 23 Mar | ✅ Done | admin_dashboard.js
T-032 | Site Navigation | Consistent nav bar across all pages with active link indicator | YoungHyun | UI/UX | 22 Mar | 24 Mar | ✅ Done | variables.css: .nav-links a.active
T-033 | Site Navigation | Hover CSS state on nav items | YoungHyun | UI/UX | 09 Mar | 09 Mar | ✅ Done | .nav-links a:hover in variables.css
T-034 | External Resources | Add jQuery 3.7.1 CDN to register.html | YoungHyun | Setup | 24 Mar | 24 Mar | ✅ Done | code.jquery.com/jquery-3.7.1.min.js
T-035 | README | Add external resources section (jQuery, Google Fonts, Material Icons) | YoungHyun | Docs | 24 Mar | — | ⚠️ Pending | To be added before submission
T-036 | README | Add assignment progress plan / timeline table | YoungHyun | Docs | 24 Mar | — | ⚠️ Pending | To be added before submission
T-037 | README | Add each member's contribution summary | YoungHyun | Docs | 24 Mar | 24 Mar | ✅ Done | Already in README.md

## Timeline
KIT502 Assignment 1 — Work Timeline (Mar 2026)
Member | Task | Mar 5 | Mar 6 | Mar 7 | Mar 8 | Mar 9 | Mar 10 | Mar 11 | Mar 12 | Mar 13 | Mar 14 | Mar 15 | Mar 16 | Mar 17 | Mar 18 | Mar 19 | Mar 20 | Mar 21 | Mar 22 | Mar 23 | Mar 24
YoungHyun | Project Setup & Structure | ■ | ■ | ■ | ■ | ■
YoungHyun | DB ERD & Schema Design | [6 empty] | ■ | ■ | ■ | [9 empty] | ■ | ■
YoungHyun | README & Documentation |  |  |  |  | ■ | ■ | ■
YoungHyun | Figma Prototype Link | [6 empty] | ■ | ■ | ■ | ■ | ■
YoungHyun | Login Page Implementation | [17 empty] | ■ | ■ | ■
YoungHyun | Signup Validation & Nav Fix | [17 empty] | ■ | ■ | ■
Gunneet | Landing Page (HTML/CSS) |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
Gunneet | Events Page (HTML/CSS) |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
Gunneet | Assets Upload & Refinement | [12 empty] | ■ | ■ | ■ | ■
Pragun | Create Event Page |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
Pragun | Manage Events Page + JS | [6 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
Pragun | Admin Dashboard + JS | [6 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
Pragun | events.json / users.json | [17 empty] | ■ | ■
Sidd | Register Page UI + jQuery | [17 empty] | ■
Sidd | Login Page UI | [17 empty] | ■

## Commit History
Git Commit History
# | Date | Author | Commit Message | Category
55 | 05 Mar 2026 | Jay | Initial commit | Setup
54 | 05 Mar 2026 | JayKimyh | first commit | Setup
53 | 05 Mar 2026 | JayKimyh | fixed: README.md | Docs
52 | 07 Mar 2026 | JayKimyh | feature: add the color palette | Design
51 | 09 Mar 2026 | JayKimyh | Feat: Shared.css README.md, Document Added | Setup
50 | 09 Mar 2026 | JayKimyh | Fix: wrong document guide | Docs
49 | 09 Mar 2026 | JayKimyh | Feature: Define the project structure | Setup
48 | 11 Mar 2026 | JayKimyh | docs: docs/database Diagram ERD added | Database
47 | 11 Mar 2026 | JayKimyh | docs: figma prototype add | Docs
46 | 12 Mar 2026 | JayKimyh | docs: fix the README.md | Docs
45 | 15 Mar 2026 | Pragun | figma link updated | Docs
44 | 15 Mar 2026 | Gunneet | Update index.html | Frontend
43 | 15 Mar 2026 | Gunneet | Create events.html | Frontend
42 | 15 Mar 2026 | Gunneet | Create landing.css | Frontend
41 | 15 Mar 2026 | Gunneet | Create events.css | Frontend
40 | 16 Mar 2026 | Pragun | create_event w/o css -u | Event Mgmt
39 | 16 Mar 2026 | Gunneet | Update index.html | Frontend
38 | 16 Mar 2026 | Gunneet | Update events.html | Frontend
37 | 16 Mar 2026 | Gunneet | Update events.css | Frontend
36 | 16 Mar 2026 | Gunneet | Update landing.css | Frontend
35 | 16 Mar 2026 | Gunneet | Update variables.css | Frontend
34 | 16 Mar 2026 | Gunneet | Add files via upload | Assets
33 | 18 Mar 2026 | Pragun | Modified create_event.html | Event Mgmt
32 | 18 Mar 2026 | Pragun | Merge remote-tracking branch 'origin/main' into pragun | Merge
31 | 18 Mar 2026 | Pragun | Resolve merge conflicts by restoring deleted files from main | Merge
30 | 20 Mar 2026 | Gunneet | Add files via upload | Assets
29 | 20 Mar 2026 | Gunneet | Add files via upload | Assets
28 | 21 Mar 2026 | JayKimyh | chore: add .gitignore | Setup
27 | 22 Mar 2026 | Pragun | created admin_dashboard html and css files | Admin
26 | 22 Mar 2026 | Pragun | modified create_event html and css file | Event Mgmt
25 | 22 Mar 2026 | Pragun | create manage_events js and css and updated the html file | Event Mgmt
24 | 22 Mar 2026 | Pragun | deleted the json file | Cleanup
23 | 22 Mar 2026 | Pragun | Merge branch 'main' into pragun | Merge
22 | 22 Mar 2026 | Pragun | modified variable css and create_event html file | Event Mgmt
21 | 22 Mar 2026 | Pragun | Added navigation link to event_html and index_html | Frontend
20 | 22 Mar 2026 | JayKimyh | Feature: nav bar fixed | UI/UX
19 | 22 Mar 2026 | JayKimyh | Feat: Make separate dummy html and relocated the html files | Frontend
18 | 22 Mar 2026 | JayKimyh | Fix: connect with dummy html files | Frontend
17 | 22 Mar 2026 | JayKimyh | Fix: manage_event.js | Event Mgmt
16 | 22 Mar 2026 | JayKimyh | Feat: Sidd made login and register pages | Auth
15 | 22 Mar 2026 | JayKimyh | Fix: nav bar | UI/UX
14 | 23 Mar 2026 | Pragun | Added: create_event.js, validation on create_event.html | Event Mgmt
13 | 23 Mar 2026 | Pragun | Updated: manage_events.html, manage_events.css and manage_events.js | Event Mgmt
12 | 23 Mar 2026 | Pragun | Added: events.json & users.json | Data
11 | 23 Mar 2026 | Pragun | Modified: fetch and display json on admin_dashboard.html & admin_dashboard.js | Admin
10 | 23 Mar 2026 | JayKimyh | Feat: login page | Auth
9 | 23 Mar 2026 | JayKimyh | Reject: create_event (reverted) | Cleanup
8 | 24 Mar 2026 | JayKimyh | Feat: Signup page, check the format | Auth
7 | 24 Mar 2026 | JayKimyh | nav bar and footer | UI/UX
6 | 24 Mar 2026 | Pragun | Updated: create_event.html | Event Mgmt
5 | 24 Mar 2026 | Pragun | Added: cancel button create_event.html | Event Mgmt
4 | 24 Mar 2026 | Pragun | Added: comments | Docs
3 | 24 Mar 2026 | JayKimyh | Fix: Database ERD and Scheme SQL | Database
2 | 24 Mar 2026 | JayKimyh | Merge branch 'main' | Merge
1 | 24 Mar 2026 | JayKimyh | Merge branch 'main' | Merge